## Sheet1
| min | max | effort
Preliminary architecture
UI design and UI ASP.NET MVC coding
Master page | 2 | 3
Projects page
Projects list page | 2.5 | 4
Create/Edit project page
Create new project/Modify submit form | 2 | 3
Project scheduling statuses list | 1 | 2
Project users' role | 2 | 3
Create new/edit scheduling status form
submit form (save data) | 2 | 3
preview Scheduled status | 3 | 5
manual SCRUM Notes send | 2 | 4
Statuses page
Status list | 2.5 | 4
Create new user status submit form (for ord.users) | 2 | 3
Users page
Users list | 2.5 | 4
Create new user submit form | 2 | 3
New users projects and roles | 1 | 2
SCRUM templates
SCRUM templates list | 1 | 2
Create/edit template form
Submit form and sending data | 2 | 3
UBB-code like tags Template validation | 3 | 5
Settings (+ config) | 1 | 2
Executive ASP.NET MVC coding | 2
Manual SCRUM sendmail + SCRUM merging | 2 | 3
Database development
Creating database tables | 1.5 | 3
Coding stored procedures
Projects list select | 1 | 1
Create/update new project | 1 | 1
Create/update new scheduled status | 1 | 1
Add/remove user role to project | 1 | 1
Select statuses list | 1 | 1
Create new status | 1 | 1
Advanced edit new status | 1 | 1
delete new status | 1 | 1
users list | 1 | 1
create/update user | 1 | 1
scrum template list | 1 | 1
create a new template | 1 | 1
SCRUM notes merging | 1.5 | 1
adding, removing jobs according schedule statuses | 3 | 5
email sending mechanism | 3 | 5
| 58.5 | 84